## Project
Task | Milestone | Status | Start date | Due date | Owner | Notes | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30 | 2026-12-07 | 2026-12-14 | 2026-12-21 | 2026-12-28 | 2027-01-04 | 2027-01-11 | 2027-01-18
Kickoff call | Discovery | Done | 2026-11-02 | 2026-11-02 | Sam
Sitemap and content plan | Discovery | Done | 2026-11-03 | 2026-11-08 | Ana
Wireframes | Design | In progress | 2026-11-09 | 2026-11-15 | Ana
Homepage design | Design | In progress | 2026-11-12 | 2026-11-19 | Lee
Design sign-off | Design | Not started | 2026-11-20 | 2026-11-22 | Client
Build page templates | Build | Not started | 2026-11-23 | 2026-12-06 | Raj
Connect forms | Build | Blocked | 2026-11-30 | 2026-12-04 | Raj
Write page copy | Content | Not started | 2026-11-23 | 2026-12-06 | Ana
Load content | Content | Not started | 2026-12-07 | 2026-12-13 | Lee
Redirects and SEO | Launch | Not started | 2026-12-14 | 2026-12-18 | Sam
QA on every device | Launch | Not started | 2026-12-21 | 2026-12-27 | Lee
Go live | Launch | Not started | 2026-12-30 | 2026-12-30 | Sam

## How to use
Gantt chart and project tracker template, from Waypoint by Codified (codified.dev/waypoint)
1. Replace the sample tasks on the Project sheet. Keep one row per task.
2. Give each task a Milestone, a Status (Not started, In progress, Blocked or Done), a Start date and a Due date.
3. The weekly grid colours itself: purple for planned or in progress, green for done, orange for blocked.
4. To change the weeks, edit the first date in the grid header and copy the next ones as +7 days.
Want clients to follow along? Upload this file to Waypoint (waypoint.codified.dev) and share a live link. Milestones become stops on the journey.